## Main
| SDO7 | PROPERTY MANAGEMENT SYSTEM
Tasks |  |  | Chulanga Averil |  |  | Kasundi Maneesha |  |  | Poornami Wijekoon |  |  | Baratha Aberathna
Number |  | Description | Estimate | Actual |  | Estimate | Actual |  | Estimate | Actual |  | Estimate | Actual
Task 1 |  | Requirements Gathering & Documentation
| 1.1 | Preparing Resume & Cover letter | 6 | 5 |  | 5 | 4 |  | 6 | 4 |  | 5 | 3
| 1.2 | Collect information about the project | 6 | 5 |  | 6 | 4 |  | 5 | 4 |  | 4 | 3
| 1.3 | Research project related topics | 7 | 6 |  | 6 | 4 |  | 4 | 4 |  | 5 | 4
| 1.4 | Prepare draft SRS | 9 | 7 |  | 8 | 6 |  | 7 | 6 |  | 8 | 2
| 1.5 | Prepare draft TA | 9 | 8 |  | 8 | 7 |  | 3 | 4 |  | 8 | 2
| 1.6 | Prepare final SRS | 10 | 9 |  | 7 | 5 |  | 6 | 5 |  | 8 | 2
| 1.7 | Prepare final TA | 12 | 10 |  | 10 | 11 |  | 9 | 9 |  | 8 | 2
Task 2 |  | Designing diagrams
| 2.1 | Design usecase diagram for system | 7 |  |  | 6 |  |  | 6 | 5 |  | 5
| 2.2 | Design class diagram for system | 8 |  |  | 5 |  |  | 6 |  |  | 5
| 2.3 | Design High Level diagram for system | 8 |  |  | 6 |  |  | 5 | 5 |  | 5
Task 3 |  | Learn tools and concepts
| 3.1 | Learn agile-scrum methodologies | 8 | 7 |  | 4 | 3 |  | 3 | 4 |  | 2 | 2
| 3.2 | Learn about Github functionalities | 9 | 9 |  | 5 | 4 |  | 3 | 5 |  | 4 | 4
| 3.3 | Learn about trello functionalities | 7 | 6 |  | 4 | 3 |  | 4 | 3 |  | 2 | 1
| 3.4 | Learn development technologies (mobile+web) | 9 |  |  | 7 |  |  | 7 | 3 |  | 8
| 3.5 | Learn language development technologies | 10 |  |  | 3 |  |  | 4 | 3 |  | 5
Task 4 |  | Design main GUI's of property mangement system
| 4.1 | Study design techniques and design requirements of system | 8 | [5 empty] | 6
| 4.2 | Design main theme of system |  |  |  | 6
| 4.3 | Design home GUI
| 4.4 | Integrate GUI's into one system and connect each of them | [9 empty] | 10
| 4.5 | Finalize and test all the functions of system | 9 |  |  | 8 |  |  | 9 |  |  | 8
Task 5 |  | Backend design and implement database
| 5.1 | Create ER digarm | 6 |  |  | 6 |  |  | 6 |  |  | 6
| 5.2 | Learn about mySQL functionalities | 4 |  |  | 4 |  |  | 4 |  |  | 4
| 5.3 | Create scripts in mySQL | 3 |  |  | 3 |  |  | 3 |  |  | 3
| 5.4 | Execute scripts and implement database | 2 |  |  | 2 |  |  | 2 |  |  | 2
Task 6 |  | Property Management of Property Management System
| 6.1 | Conducting a research and gather information about the property management system | 14 | 12
| 6.2 | Clarifying the functional and non functional requirements by meeting the client. | 6 | 3
| 6.3 | Drawing the necessary UML diagrams according to the function | 12
| 6.4 | Designing GUI according to the specified requirements | 13
| 6.5 | Selecting color code and icons for GUI | 6
| 6.6 | Implementing CRUD functions | 13
| 6.7 | Coding other necessary functions | 10
| 6.8 | Create and execute scripts in mySQL database | 9
| 6.9 | Testing and finalizing the function | 8
Task 7 |  | Booking Management of Property Management System
| 7.1 | Studying required coding technologies and gather tenant requirements | [6 empty] | 8 | 7
| 7.2 | Designing wireframes for booking management GUIs | [6 empty] | 6 | 6
| 7.3 | Selecting appropriate color codes and icons for Booking Management GUIs | [6 empty] | 4 | 3
| 7.4 | Designing GUIs for selected requirements and specifications | [6 empty] | 15 | 16
| 7.5 | Creating functions to add and view bookings | [6 empty] | 6
| 7.6 | Creating functions to delete and update bookings | [6 empty] | 12
| 7.7 | Creating function to calculate payments,monthly rentals of the tenants | [6 empty] | 10
| 7.8 | Generating an invoice including payment details | [6 empty] | 8
| 7.9 | Creating and executing scripts in mySQL database | [6 empty] | 9
| 7.1 | Testing and finalizing the function | [6 empty] | 7
Task 8 |  | User Management of Property Management System
| 8.1 | Create function break down list | [9 empty] | 10 | 9
| 8.2 | Draw use case diagram | [9 empty] | 5 | 6
| 8.3 | Create table design scheme | [9 empty] | 5 | 6
| 8.4 | Research about User types of the system | [9 empty] | 5 | 5
| 8.5 | Design wireframe user profile | [9 empty] | 6 | 8
| 8.6 | Design wireframe login | [9 empty] | 6 | 4
| 8.7 | Design GUI's | [9 empty] | 13
Task 9 |  | Bookmark and Save in Property Management System
| 9.1 | Create function break down list | [9 empty] | 10 | 9
| 9.2 | Draw use case diagram | [9 empty] | 5 | 6
| 9.3 | Create table design scheme | [9 empty] | 5 | 6
| 9.4 | Research about UX in bookmarking,Save property | [9 empty] | 6 | 5
| 9.5 | Design wireframe my bookmarks | [9 empty] | 8 | 8
| 9.6 | Design GUI's | [9 empty] | 13
| 9.7 | Ajax review for bookmark function | [9 empty] | 6
Task 10 |  | Review and Commenting in Property Management System
| 10.1 | Study about review and commenting function details and functional requirements |  |  |  | 10 | 8
| 10.2 | Design wireframe for Review and commenting GUI |  |  |  | 5 | 4
| 10.3 | Select appropriate colors and icons for Review and commenting GUI |  |  |  | 6
| 10.4 | Design GUI of Review and commenting |  |  |  | 14
| 10.5 | Create functions to add and view reviews and comments |  |  |  | 9
| 10.6 | Create functions to delete and update reviews and comments |  |  |  | 8
| 10.7 | Create functions to rate the system |  |  |  | 7
| 10.8 | Create other necessary functions |  |  |  | 9
| 10.9 | Create and execute scripts in mySQL database |  |  |  | 8
| 10.1 | Test and finalize function |  |  |  | 6
Task 11 |  | Search in Property Management System
| 11.1 | Gathering search management function details and requirements | [6 empty] | 9 | 6
| 11.2 | Designing wireframes for search management | [6 empty] | 6 | 4
| 11.3 | Select appropriate colors and icons for Search Management GUI | [6 empty] | 4 | 3
| 11.4 | Designing GUIs for Search management function | [6 empty] | 8 | 8
| 11.5 | Implementing CRUD functions | [6 empty] | 10
| 11.6 | Creating other required codes for the function | [6 empty] | 9
| 11.7 | Creating and executing scripts in mySQL database | [6 empty] | 8
| 11.8 | Testing and finalizing function | [6 empty] | 6
Task 12 |  | Preferences Management in Property Management System
| 12.1 | Search for preference management function details and requirements |  |  |  | 9 | 6
| 12.2 | Study required GUI design tehnologies for function and design wireframe |  |  |  | 7 | 5
| 12.3 | Select appropriate icons and colors for GUI |  |  |  | 4
| 12.4 | Design GUI of preferences management for selected guidelines |  |  |  | 14
| 12.5 | Create functions to get user preferences and sort it in results |  |  |  | 10
| 12.6 | Create other required functions |  |  |  | 9
| 12.7 | Create and execute scripts in mySQL database |  |  |  | 8
| 12.8 | Test and finalize function |  |  |  | 5
|  |  | 248 | 87 | 0 | 235 | 74 | 0 | 253 | 117 | 0 | 218 | 97 | 0
Approval of the supervisor:
Note on A3: Author: Tasks can be shown in several ways. Each of the examples below is acceptable. In general, the right-most column should be the lowest-level task numbers and all other task number components should be in the left-hand column.
Note on D114: Author: If you are inserting rows (as you probably will) make sure that these totals capture all of the contents. Remember that you are expecting to work 10 hours per week per 25 credits of unit, and you have around 14 weeks to work with per semester.